## Sheet1
Stage ID | Task | Start Date | Duration
1 | (CORE) Research | 2019-02-04 | 7
1.1 | (CORE) Requirement gathering/review | 2019-02-11 | 14
1.2 | (CORE) Stage/Time Allocation Planning | 2019-02-18 | 7
1.3 | (CORE) Processor specification, architecture, ISA | 2019-02-25 | 100
2.1 | (CORE) Decoder, Register Set, impl & integration | 2019-02-25 | 14
2.2 | (CORE) Register set impl & integration | 2019-03-04 | 14
2.3 | (CORE) Local memory impl & integration | 2019-03-11 | 14
X | Intense Coursework/Test month | 2019-03-04 | 31
3.1 | (CORE) Memory mapped register layout & impl | 2019-04-01 | 21
3.2 | (CORE) Wishbone peripheral bus connected to MMU | 2019-04-08 | 21
3.3 | (CORE) Pipelined implementation and verification | 2019-04-15 | 21
3.4 | (CORE) Cache memory design & impl
X | Intense Coursework/Exam month | 2019-05-01 | 31
4.1 | (CORE) Multi-core communication interface | 2019-06-05 | 28
4.2 | (CORE) Shared-memory controller | 2019-06-05 | 28
4.3 | (CORE) Scalable multi-core interface (10s of cores) | 2019-07-01 | 28
4.4 | (CORE) Multi-core example program (reduction) | 2019-07-10 | 7
5.1 | (EXT) SPI-FPGA interface for OTG programming |  | 14
5.2 | (EXT) FPGA-PC interfacing |  | 28
5.3 | (EXT) FPGA-PC debugging (instruction breakpoints) |  | 28
6.1 | (EXT) Compiler backend for vmicro16 |  | 7
6.2 | (EXT) Compiler support for multi-core codegen |  | 21
7.1 | (CORE) Wishbone peripherals for demo | 2019-08-01 | 14
8 | Final Report | 2019-06-05 | 70